## Gantt Chart
GANTT CHART - CS401 Software Eng.
PROJECT TITLE |  | Blackjack |  |  |  |  | COMPANY NAME | [6 empty] | TBD
ORIGINAL PROJECT MEMBERS |  | JianTing Tan / Zhenwen Wang / Isabell Ampon |  |  |  |  | DATE | [6 empty] | 2020-01-21
CURRENT PROJECT MEMBERS |  | Ivan Peric / Alvin Derek Tiletile / Yew Loon Mun |  |  |  |  | TAKEOVER DATE | [6 empty] | 2020-04-06
WBS NUMBER | TASK TITLE |  | START DATE | DUE DATE | DURATION | TASK COMPLETE? (Y/N) | PHASE ONE | [9 empty] | PHASE TWO | [29 empty] | PHASE THREE | [9 empty] | PHASE FOUR | [9 empty] | PHASE FIVE
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Select Team Members |  | 2020-01-21 | 2020-02-04 | 13 | Y | bar: WEEK 1 M to WEEK 2 F
1.2 | Select Project |  | 2020-01-21 | 2020-02-04 | 13 | Y | bar: WEEK 1 M to WEEK 2 F
1.3 | Create Project Docs |  | 2020-01-21 | 2020-02-04 | 13 | Y | bar: WEEK 1 M to WEEK 2 F
1.4 | Create Repo |  | 2020-01-21 | 2020-02-04 | 13 | Y | bar: WEEK 1 M to WEEK 2 F
1.5 | High Level Abstract |  | 2020-01-21 | 2020-02-04 | 13 | Y | bar: WEEK 1 M to WEEK 2 F
2 | Project Definition and Planning
2.1 | UML Project Design |  | 2020-02-07 | 2020-02-21 | 14 | Y | bar: WEEK 3 M to WEEK 8 F
2.1.2 | UML Finalization |  | 2020-02-12 | 2020-02-21 | 9 | Y | bar: WEEK 3 M to WEEK 8 F
2.2 | Project Requirements Doc |  | 2020-02-07 | 2020-02-21 | 14 | Y | bar: WEEK 3 M to WEEK 8 F
2.3 | Gantt Chart |  | 2020-02-07 | 2020-02-21 | 14 | Y | bar: WEEK 3 M to WEEK 8 F
2.4 | Roles & Responsibilities Doc |  | 2020-02-07 | 2020-02-21 | 14 | Y | bar: WEEK 3 M to WEEK 8 F
2.5 | Finalize All Documentation |  | 2020-03-02 | 2020-03-17 | 15 | Y | bar: WEEK 3 M to WEEK 8 F
3 | Project Instantiation
3.1 | Work on Deck Object |  | 2020-03-17 | 2020-04-06 | 19 | x
3.2 | Work on Card Object |  | 2020-03-17 | 2020-04-06 | 19 | x
3.3 | Work on Player Object |  | 2020-03-17 | 2020-04-06 | 19 | x
3.4 | Work on Money Object |  | 2020-03-17 | 2020-04-06 | 19 | x
3.5 | Work on Rules Database |  | 2020-03-17 | 2020-04-06 | 19 | x
3.6 | Work on Authentification Database |  | 2020-03-17 | 2020-04-06 | 19 | x
4 | Project Instantiation (Part 2)
4.1 | Create a Software Test Plan |  | 2020-04-06 | 2020-04-10 | 4 | x
4.1.2 | Document Test Cases |  | 2020-04-06 | 2020-04-10 | 4 | x
4.1.3 | Plan out project test suite |  | 2020-04-06 | 2020-04-10 | 4 | x
4.1.4 | Code jUnit tests |  | 2020-04-06 | 2020-04-10 | 4 | x
4.2 | Plan Prototypes |  | 2020-04-06 | 2020-04-10 | 4 | x
4.3 | Ensure Skeleton Classes are complete |  | 2020-04-06 | 2020-04-10 | 4 | x
4.4 | TBD |  | 2020-04-06 | 2020-04-10 | 4 | x
5 | Project Instantiation (Part 3)
5.1 | TBD |  | 2020-04-21 | 2020-04-28 | 7 | x
5.1.2 | TBD |  | 2020-04-21 | 2020-04-28 | 7 | x
5.3 | TBD |  | 2020-04-21 | 2020-04-28 | 7 | x
5.4 | TBD |  | 2020-04-21 | 2020-04-28 | 7 | x
6 | Project Performance + Monitoring
6.1 | TBD |  | 2020-04-28 | 2020-05-09 | 11 | x
6.2 | TBD |  | 2020-04-28 | 2020-05-09 | 11 | x
6.3 | TBD |  | 2020-04-28 | 2020-05-09 | 11 | x
6.4 | TBD |  | 2020-04-28 | 2020-05-09 | 11 | x